POWER PLATFORM Architecture Starter Kit The production-ready blueprint for enterprise tenants

| Includes - Reference Architecture Overview - Environment Strategy Checklist - DLP Policy Design Templates - ALM Pipeline Checklist - Production Readiness Assessment | Designed for - Solution Architects - Lead Technical Consultants - CoE Leads & Platform Owners - Power Platform Practice Leads - Enterprise Architects |
| --- | --- |

v1.0  |  2026 Edition

Power Platform Architecture Starter Kit

# How to use this kit

This starter kit gives you five reusable tools for designing, reviewing, and governing a Power Platform enterprise tenant. Use it as a starting point — adapt the checklists to your organisation's policies and add your own standards.

| Tool | Use it when | Time to complete | Audience |
| --- | --- | --- | --- |
| 1. Reference Architecture | Starting a new tenant or reviewing an existing one | 60–90 min review | Architect, Platform Owner |
| 2. Environment Checklist | Provisioning any new environment | 15–30 min per env | Architect, CoE Admin |
| 3. DLP Templates | Designing or auditing DLP policy stack | 1–2 hours | Architect, Security Lead |
| 4. ALM Checklist | Before go-live for any production workload | 30–45 min per workload | Architect, Lead Dev |
| 5. Production Readiness | Pre-go-live gate review | 2–3 hours full review | Architect, Stakeholder |

| ARCHITECT TIP | Start with Tool 5 (Production Readiness Assessment) on an existing tenant. The gaps it surfaces tell you exactly which of the other tools to prioritise. |
| --- | --- |

## Recommended usage sequence

- Greenfield tenant: Tools 1 → 2 → 3 → 4 → 5 (in order)

- Existing tenant review: Tool 5 first, then address gaps using Tools 1–4

- Per-workload delivery: Tools 2 + 4 for every new workload deployment

- Governance audit: Tools 3 + 5 annually or after major policy changes

Tool 1 — Reference Architecture Overview The seven-layer production tenant model

The diagram below describes the logical architecture of a production-ready Power Platform tenant. Each layer is independent but interdependent — a gap in any layer creates risk in the others.

| Layer | Components | Key decision |
| --- | --- | --- |
| 1. Identity & Admin | AAD groups, Managed Environments, Power Platform Admin Centre, RBAC | Who owns what — establish group structure before provisioning environments |
| 2. Environment Topology | Default (locked), Dev, UAT, Prod, CoE, Shared Services | How many environments — map to workloads, not teams or individuals |
| 3. DLP Policy Stack | Tenant-wide baseline, env-tier policies, connector classification | What connectors are allowed where — tiered, not one-size-fits-all |
| 4. ALM Pipeline | Solutions, Azure DevOps / PP Pipelines, deployment gates, solution checker | Unmanaged in dev, managed in prod — enforce this at the pipeline level |
| 5. Data Layer | Dataverse, SharePoint, Azure SQL, virtual tables, storage capacity | Dataverse per workload vs shared — decide based on data classification |
| 6. Integration Layer | Azure APIM, Service Bus, Azure Functions, custom connectors | Where does complexity live — Power Automate vs Azure depends on SLA requirements |
| 7. Observability | Application Insights, CoE dashboards, Power BI, flow run alerts | What does production failure look like — define before go-live, not after |

## Environment topology detail

| Environment | DLP tier | Who has access | Managed? | Solution policy |
| --- | --- | --- | --- | --- |
| Default | Restrictive | All licensed users (read-only) | Required | No solutions deployed |
| Developer (personal) | Standard | Individual maker only | Recommended | Unmanaged only, auto-expire 90 days |
| Team Dev | Standard | Workload team + architects | Recommended | Unmanaged, source-controlled |
| UAT / QA | Production-equivalent | QA team + workload lead | Required | Managed solutions only |
| Production | Strict | Service accounts + break-glass | Required | Managed solutions only, change-gated |
| CoE Admin | Elevated (CoE connectors) | CoE team only | Required | CoE kit + custom governance flows |
| Shared Services | Standard | All architects | Required | Managed, versioned shared components |

| ANTI-PATTERN | Anti-pattern: deploying unmanaged solutions to production. This is the single most common architectural failure in Power Platform projects. Enforce managed-only in all environments at UAT and above using Managed Environments solution checker policy. |
| --- | --- |

## AAD group structure

| AAD group name pattern | Power Platform role | Notes |
| --- | --- | --- |
| PP-GlobalAdmins | Power Platform Administrator | Service accounts only. No named users. MFA enforced. |
| PP-EnvAdmin-{WorkloadName} | Environment Administrator | Lead architect or workload owner per environment. |
| PP-Makers-{WorkloadName} | Environment Maker | Pro-devs and citizen developers assigned per project. |
| PP-CoE-Admins | CoE env full access | Central governance team only. Separate from workload admins. |
| PP-ReadOnly-{WorkloadName} | System Customizer (read) | Architects reviewing environments without edit rights. |
| PP-BreakGlass | Power Platform Administrator | Emergency access. Use logged, reviewed quarterly. |

Tool 2 — Environment Strategy Checklist Run this for every new environment before provisioning

Complete this checklist before provisioning any environment. Items marked Required must be in place before makers are granted access. Items marked Recommended should be addressed within 30 days.

## Pre-provisioning decisions

| Decision / action | Priority | Owner |
| --- | --- | --- |
| Environment purpose documented (dev / UAT / prod / CoE / sandbox) | Required | Architect |
| Environment named using tenant naming convention (PREFIX-WORKLOAD-TIER) | Required | CoE Admin |
| Region selected — matches Dataverse region and data residency requirements | Required | Architect |
| AAD groups created and mapped to environment roles before access granted | Required | Identity Admin |
| DLP policy tier assigned (restrictive / standard / strict) | Required | Architect |
| Managed Environments enabled (UAT and Prod mandatory) | Required | Platform Admin |
| Dataverse provisioned only if required — do not provision by default | Required | Platform Admin |
| Storage capacity allocated and monitored | Recommended | CoE Admin |
| Environment description and owner recorded in CoE inventory | Recommended | CoE Admin |
| Auto-expiry configured for developer sandboxes (90-day policy) | Recommended | CoE Admin |
| Audit logging enabled (Dataverse environments) | Recommended | Platform Admin |
| Usage analytics baseline captured (CoE Power BI report) | Optional | CoE Admin |

## Post-provisioning validation

| Validation step | Priority | Owner |
| --- | --- | --- |
| Confirm correct DLP policy is applied and inherited | Required | Architect |
| Verify AAD group membership — no individual user assignments | Required | Identity Admin |
| Test maker access with a non-admin account before broad rollout | Required | CoE Admin |
| Confirm solution checker policy is enforced (Managed Environments) | Required | Platform Admin |
| Confirm no unintended connectors accessible from this environment | Required | Architect |
| Add environment to CoE monitoring scope | Recommended | CoE Admin |
| Document connection references and environment variables required | Recommended | Lead Developer |
| Confirm service account has access and valid connections | Required | CoE Admin |

## Environment capacity planning guide

| Workload type | Dataverse storage (est.) | Min capacity add-on | Review frequency |
| --- | --- | --- | --- |
| Simple canvas app + SharePoint | None required | None | Annual |
| Model-driven app, <1,000 records/table | 1–5 GB | None (included) | Quarterly |
| Model-driven app, 10k–100k records/table | 10–50 GB | 1–5 GB add-ons | Monthly |
| Enterprise data platform, 1M+ records | 100 GB+ | 10+ GB add-ons | Weekly alert |
| Document processing (AI Builder) | Variable — log data | Monitor AI credits too | Monthly |

Tool 3 — DLP Policy Design Templates Five-tier connector policy stack for enterprise tenants

Data Loss Prevention policies in Power Platform operate as a layered stack. Tenant-level policies apply everywhere. Environment-level policies are additive restrictions on top. Use the five templates below as your starting point and adjust based on your organisation's risk appetite.

## Policy stack overview

| Policy tier | Scope | Override possible? | Purpose |
| --- | --- | --- | --- |
| Tier 0 — Global baseline | All environments | No | Block highest-risk connectors tenant-wide. Cannot be undone by environment admins. |
| Tier 1 — Default env | Default environment only | No | Restrict to Microsoft 365 connectors only. Prevents shadow IT in the Default environment. |
| Tier 2 — Developer / sandbox | Dev and sandbox envs | By architects only | Broader access for building. Allows most Microsoft-published connectors. |
| Tier 3 — UAT / production | UAT and Prod envs | Via change management | Approved connector list only. Any addition requires architecture review. |
| Tier 4 — CoE admin env | CoE environment only | No (scoped tightly) | Elevated access for CoE flows. HTTP, Management connector, Admin APIs. |

## Connector classification guide

| Connector | Tier 0 | Tier 1 | Tier 2 | Tier 3/4 | Classification |
| --- | --- | --- | --- | --- | --- |
| SharePoint, Outlook, Teams, OneDrive | Business | Business | Business | Business | Microsoft 365 — always business |
| Dataverse | Business | Business | Business | Business | Core platform — always business |
| Power BI, Excel Online, Forms | Business | Business | Business | Business | Microsoft 365 — always business |
| Azure Blob, SQL, Service Bus | Business | Blocked | Business | Business | Azure — allow from Tier 2+ |
| HTTP with Azure AD | Blocked | Blocked | Business (reviewed) | Business | High risk — review each use case |
| HTTP (anonymous) | Blocked | Blocked | Blocked | Blocked | Block everywhere |
| Salesforce, ServiceNow, SAP | Non-Business | Blocked | Non-Business | Business (approved) | 3rd party — case-by-case review |
| Approvals, Notifications | Business | Business | Business | Business | Platform — always business |
| Custom connectors (reviewed) | Non-Business | Blocked | Non-Business | Business (reviewed) | Require security review + approval |
| Custom connectors (unreviewed) | Blocked | Blocked | Blocked | Blocked | Block until reviewed |

## Connector request process

When a maker requests a connector not currently in the business tier, follow this process:

- Maker submits connector request via CoE environment request app (include: connector name, use case, target environment, data sensitivity)

- CoE admin reviews against approved connector registry — is it already approved in another environment?

- Security review: does the connector access external services? What data will flow through it? Is OAuth used?

- Architect decision: approve for specific environment only, add to standard approved list, or reject with alternative

- If approved: update DLP policy for target environment, document in connector registry, notify maker

- If rejected: provide an alternative connector or architecture pattern that achieves the same outcome

| CAUTION | Never grant connector exceptions at the tenant level to solve an environment-level problem. A connector approved for one project will be accessible to every maker in every environment. Always scope to the specific environment. |
| --- | --- |

Tool 4 — ALM Pipeline Checklist Pre-deployment gates for every production workload

Application Lifecycle Management is the discipline that separates an enterprise Power Platform deployment from a personal productivity tool. This checklist covers solution strategy, pipeline configuration, and deployment gates. Complete before any workload reaches UAT.

## Solution design checklist

| Checklist item | Priority | Verified by |
| --- | --- | --- |
| Publisher created with correct prefix (no default publisher in production) | Required | Architect |
| Solution created using workload publisher — not default | Required | Lead Developer |
| All components are inside a solution — no orphaned customisations | Required | Lead Developer |
| Solution display name follows naming standard (WORKLOAD - Component Type) | Recommended | Lead Developer |
| Environment variables used for all environment-specific values (URLs, IDs, etc.) | Required | Lead Developer |
| Connection references created for all connectors — no hardcoded connections | Required | Lead Developer |
| Canvas apps saved with explicit names — no 'App' or 'Canvas App 1' | Recommended | Lead Developer |
| All flows disabled in source environment before export if required in target | Recommended | Lead Developer |
| Dependencies on shared components referenced as separate managed solution (layer pattern) | Recommended | Architect |

## Pipeline configuration checklist

| Checklist item | Priority | Verified by |
| --- | --- | --- |
| Source control configured — solutions exported and committed on every change | Required | Lead Developer |
| Solution Checker runs automatically on export — errors block deployment | Required | Architect |
| Automated export pipeline triggers on solution version increment | Recommended | Lead Developer |
| Deployment pipeline configured: Dev → UAT (managed) → Prod (managed) | Required | Architect |
| UAT deployment requires lead architect approval before proceeding | Required | Architect |
| Production deployment requires business stakeholder sign-off | Required | Architect |
| Environment variable values documented per deployment target | Required | Lead Developer |
| Connection reference ownership documented — named owner per connection | Required | CoE Admin |
| Post-deployment smoke test automated (flow trigger → validate → alert on fail) | Recommended | Lead Developer |
| Rollback procedure documented and tested before first production deployment | Required | Architect |

## Tooling decision guide

| Scenario | Recommended tool | When to upgrade |
| --- | --- | --- |
| Small team (<5 devs), simple workloads | Power Platform Pipelines (built-in) Low complexity, no DevOps licence needed | When you need branch strategy or multi-approver gates |
| Medium team, multiple workloads in parallel | Azure DevOps + Power Platform Build Tools Full pipeline control, environment gates, PR workflows | When deploying to regulated environments (ISO, HIPAA) |
| Enterprise, regulated industry | Azure DevOps + custom pipeline + SonarQube Full audit trail, security scanning, compliance gates | Already at the top — focus on maturity not tooling |
| GitHub-native teams | GitHub Actions + microsoft/powerplatform-actions Same capability as Azure DevOps, GitHub native | When organisation standardises on Azure DevOps |

Tool 5 — Production Readiness Assessment Score your tenant across six domains before go-live

Use this assessment as a pre-go-live gate review. Score each item and calculate the domain score. A domain scoring below 70% should be addressed before production launch. A domain scoring below 50% is a go/no-go blocker.

| Scoring | Score | Gate | Action |
| --- | --- | --- | --- |
| 80–100% | Production ready | Recommended | Proceed to go-live |
| 70–79% | Conditionally ready | Optional | Address gaps within 30 days post go-live |
| 50–69% | Needs work | Optional | Address critical items before go-live |
| Below 50% | Not ready | Avoid | Go/no-go blocker — do not proceed |

## Domain 1: Identity & Access Management

| Assessment item | Priority | Status | Owner |
| --- | --- | --- | --- |
| All admin access uses named service accounts — no personal accounts with Power Platform Admin | Required |  |  |
| AAD groups used for all environment access — no individual user role assignments | Required |  |  |
| Break-glass admin account exists, MFA enforced, usage audited | Required |  |  |
| All production flows run under service account identity — not a named user | Required |  |  |
| Connection reference ownership documented for every production connection | Required |  |  |
| Developer environments auto-expire — no permanent personal sandboxes | Recommended |  |  |
| Domain score: _____ / 6 items complete = _____% |  | Gate status: GREEN / AMBER / RED |  |

## Domain 2: Governance & DLP

| Assessment item | Priority | Status | Owner |
| --- | --- | --- | --- |
| Tenant-wide DLP baseline policy active — high-risk connectors blocked globally | Required |  |  |
| Default environment DLP locked to Microsoft 365 connectors only | Required |  |  |
| Production environment DLP uses strict approved-list policy | Required |  |  |
| Connector request process documented and operational | Recommended |  |  |
| CoE Starter Kit deployed (core components minimum) | Recommended |  |  |
| DLP policy documentation kept in version control | Recommended |  |  |
| Domain score: _____ / 6 items complete = _____% |  | Gate status: GREEN / AMBER / RED |  |

## Domain 3: ALM & Deployment

| Assessment item | Priority | Status | Owner |
| --- | --- | --- | --- |
| All production components inside managed solutions — no unmanaged customisations | Required |  |  |
| Environment variables used for all environment-specific configuration | Required |  |  |
| Connection references used — no hardcoded connections | Required |  |  |
| Solution checker passes with zero errors before deployment | Required |  |  |
| Deployment pipeline configured with approval gates before production | Required |  |  |
| Rollback procedure documented and tested | Required |  |  |
| Source control contains current state of all solutions | Recommended |  |  |
| Domain score: _____ / 7 items complete = _____% |  | Gate status: GREEN / AMBER / RED |  |

## Domain 4: Data & Dataverse

| Assessment item | Priority | Status | Owner |
| --- | --- | --- | --- |
| Dataverse publisher prefix defined — default publisher not used in production | Required |  |  |
| Row-level security model designed and tested | Required |  |  |
| Audit logging enabled on all PII-containing or business-critical tables | Required |  |  |
| Storage capacity monitored with alert threshold configured | Recommended |  |  |
| Dataverse schema documented — table relationships and key fields | Recommended |  |  |
| Bulk delete jobs configured for transactional tables with high record volume | Recommended |  |  |
| Domain score: _____ / 6 items complete = _____% |  | Gate status: GREEN / AMBER / RED |  |

## Domain 5: Monitoring & Operations

| Assessment item | Priority | Status | Owner |
| --- | --- | --- | --- |
| Critical production flows have failure alerts configured (Teams or email) | Required |  |  |
| CoE inventory captures all production apps, flows, and their owners | Required |  |  |
| Application Insights connected for canvas apps and flows in production | Recommended |  |  |
| Operational runbook exists for common failure scenarios | Recommended |  |  |
| On-call responsibility for production Power Platform issues assigned | Required |  |  |
| Monthly governance review of stale apps and orphaned flows scheduled | Recommended |  |  |
| Domain score: _____ / 6 items complete = _____% |  | Gate status: GREEN / AMBER / RED |  |

## Domain 6: Licensing & Cost Management

| Assessment item | Priority | Status | Owner |
| --- | --- | --- | --- |
| Per-user vs per-flow decision made and documented for all production flows | Required |  |  |
| Licence consumption tracked — alert when >85% of licences assigned | Recommended |  |  |
| Dataverse storage cost included in operational budget | Required |  |  |
| AI Builder credit consumption monitored (if applicable) | Recommended |  |  |
| Licence cost model reviewed by finance stakeholder before go-live | Required |  |  |
| Licence reassignment process in place for leavers and role changes | Recommended |  |  |
| Domain score: _____ / 6 items complete = _____% |  | Gate status: GREEN / AMBER / RED |  |

## Overall readiness summary

| Domain | Score (%) | Gate | Priority actions |
| --- | --- | --- | --- |
| Identity & Access Management |  |  |  |
| Governance & DLP |  |  |  |
| ALM & Deployment |  |  |  |
| Data & Dataverse |  |  |  |
| Monitoring & Operations |  |  |  |
| Licensing & Cost Management |  |  |  |
| OVERALL TENANT READINESS |  |  |  |

What to do next You have the blueprint. Now put it into action. 1. Run Tool 5 on your current tenant The assessment surfaces your biggest gaps in under 2 hours. 2. Fix your top 3 red items Focus on Identity, ALM, and DLP — they have the highest blast radius if wrong. 3. Read the deep-dive blog posts Each tool in this kit has a full companion article on the blog. 4. Subscribe for updates New tools, templates, and architecture deep-dives published weekly.

Questions or feedback on this kit?

Power Platform Architecture Kit  |  2026